## Slide 1
STARTUPLAB
User Acceptance Testing
Progress and Decision Presentation
Loan Star Lending Group Company.
UAT Date: 09/22/2026 | | Prepared by Rovick Romasanta
01
Notes: HOW TO USE THIS SLIDE
Use this cover for the formal client UAT session. Confirm the project name, client, date, tested version, and presenter.
SUGGESTED CLIENT-FACING WORDING
Good [morning/afternoon]. Today we will review the project progress, validate the agreed solution, record the results, and confirm the next step.

## Slide 2
STARTUPLAB
ORIENTATION
02
UAT presentation flow
The presentation covers project progress before moving into client validation and approval.
01
PROJECT PROGRESS
Objective, scope, timeline, completed work
02
UAT READINESS
Environment, users, data, scenarios
03
CLIENT TESTING
Execute scenarios and record evidence
04
DECISION
Results, actions, approval, next step
Keep the project story short enough to leave most of the session for client testing and decisions.
Notes: HOW TO USE THIS SLIDE
Use this slide as the agenda. State that the client will see the complete project status before testing begins.
SUGGESTED CLIENT-FACING WORDING
We will first confirm what the project set out to deliver and where it stands. We will then complete the UAT cycle and agree on the decision and follow-up actions.

## Slide 3
STARTUPLAB
PROJECT PROGRESS
03
Project overview
Summarize the business reason for the project before discussing features or technical details.
Topic | Information to Present | Client Confirmation
Business problem | Manual, paper-based processing across CSA, CIG, Committee, LRA, AR, and Collector teams — no unified system to track a file. | Confirm or revise
Project objective | Confirm the platform performs borrower onboarding, underwriting, committee review, release, collections, accounting, admin, and access control correctly before handover. | Confirm
Primary users | Borrowers & Agents (Seafarer/SME/Individual); CSA, CIG, Committee, LRA, Collector, AR, Remedial, Admin staff; Management/Executives. | Confirm
Solution delivered | Unified digital lending platform: origination, underwriting, committee decisions, disbursement, servicing, collections, and reporting. | Confirm
Project Owner | Rovick Romasanta | Acknowledge
Authorized approver | Client approver — Jemmy Hsieh/Rene – Rovick Romasanta | Confirm authority
The Project Owner presents verified records and coordinates with the CEO when approval exceeds assigned authority.
Notes: HOW TO USE THIS SLIDE
Use plain business language. Do not begin with technical architecture unless the client asks for it.
SUGGESTED CLIENT-FACING WORDING
This project started because [business problem]. The agreed objective was [objective]. Today we will validate whether the completed solution supports that objective.

## Slide 4
STARTUPLAB
PROJECT PROGRESS
04
Approved scope and success criteria
Set the testing boundary before showing progress or accepting new requests.
Area | Approved Requirement or Measure | Status / Evidence
Included scope | 14 modules / 5 areas: Onboarding (Registration, Borrower Portal, Agent Leads); Underwriting (CSA, CIG, Committee, LRA); Servicing (Briefings, AR, Collector DCR, Remedial); Admin (Reports, Dashboard, Users); Controls (Auth, RBAC, Redirects). | UAT Plan Appendix A, POL-006
Out of scope | footer Legal pages (placeholder links); session persistence via standard browser cookies only. | Approved for this release
Success measure 1 | A case in Appendix B is Passed only when the actual result matches the expected result exactly. | POL-006 section 8.4
Success measure 2 | A module is accepted when all its cases are Passed or Accepted with Minor Actions. | POL-006 section 8.4
Acceptance basis | POL-006 UAT and Final Project Handover Policy — Appendix A & B. | Appendix A/B, POL-006
Known limitation | The three items above are accepted limitations for this release. | Client acknowledgment pending
Record new requests separately. Assess scope, cost, timeline, and risk before making a commitment.
Notes: HOW TO USE THIS SLIDE
Confirm the baseline that UAT will validate. If the client disputes the scope, stop and reconcile the approved records.
SUGGESTED CLIENT-FACING WORDING
These are the items included in the approved project and the measures we will use during acceptance. New ideas will be recorded for assessment after the session.

## Slide 5
STARTUPLAB
PROJECT PROGRESS
05
Project timeline and current position
Show the client how the project moved from approval to UAT.
1
DISCOVERY
Approved requirements & 14-module scope
2
DESIGN
Design system UI/UX finalized
3
BUILD
14 modules built end to end
4
INTERNAL TEST
TBD
Internal QA & E2E simulation done
5
UAT
110 test cases ready (Appx B)
6
HANDOVER
Signed UAT acceptance (Appx G)
Use actual approval and completion dates. Do not present estimated work as completed work.
Notes: HOW TO USE THIS SLIDE
Replace each date and output. Highlight the current UAT stage and the planned handover gate.
SUGGESTED CLIENT-FACING WORDING
The project completed the approved discovery, design, build, and internal testing activities. We are now at UAT, where your users validate the solution before final handover.

## Slide 6
STARTUPLAB
PROJECT PROGRESS
06
Overall project progress
Present completion by deliverable, supported by evidence rather than a general percentage alone.
Deliverable | Planned Output | Progress | Evidence / Comment
Borrower & Agent Onboarding | Registration, Borrower Portal, Agent Leads | Ready for UAT | UAT-001–023 ready
Underwriting Workflow | CSA Intake, CIG Verification, Committee, LRA Release | Ready for UAT | UAT-024–048, 097–110
Post-Disbursement & Servicing | Briefings, AR Ledger, Collector DCR, Remedial | Ready for UAT | UAT-049–067 ready
Management & Administration | Reports, Dashboard Hub, User & Role Mgmt | Ready for UAT | UAT-068–082 ready
System-Wide Controls | Authentication, Password Reset, RBAC, Redirects | Ready for UAT | UAT-083–096 ready
OVERALL | 14 modules, 110 UAT test cases | All modules ready for UAT | Testing dates TBD
Use a documented calculation for the overall percentage. Clearly separate completed, in progress, blocked, and deferred work.
Notes: HOW TO USE THIS SLIDE
Populate using the project tracker and approved deliverables. Explain any incomplete or deferred item and its effect on UAT.
SUGGESTED CLIENT-FACING WORDING
The project is [percentage] complete based on the approved deliverables. These items are ready for UAT, while [item] remains [status] because [reason].

## Slide 7
STARTUPLAB
PROJECT PROGRESS
07
Delivered solution overview
Connect completed features to the client’s daily work.
Business Area | Delivered Capability | User Benefit | UAT Scenario
Borrower & Agent Onboarding | Registration & account settings; Seafarer/SME/Individual intake; Agent lead pipeline | Self-service applications, faster agent conversion | UAT-001–023
Underwriting Workflow | CSA intake & computation; CIG verification (Field Visit, collateral); Committee voting; LRA release setup | Faster, auditable, consistent credit decisions | UAT-024–048, 097–110
Post-Disbursement & Servicing | Pre-departure briefings; AR masterlist & ledger; Collector DCR; Remedial portfolio | Accurate receivables, earlier delinquency response | UAT-049–067
Management & Administration | Operational reports & analytics; Dashboard Hub; staff user & role management | Real-time visibility, controlled staff access | UAT-068–082
System-Wide Controls | Authentication, password recovery, RBAC, legacy route redirection | Secure, role-gated access to every module | UAT-083–096
Keep this overview focused. The detailed validation happens in the UAT scenarios.
Notes: HOW TO USE THIS SLIDE
Use one row for each important business capability. Avoid listing technical tasks that the client cannot validate.
SUGGESTED CLIENT-FACING WORDING
The completed solution supports these business areas. Each capability connects to a UAT scenario that your users will perform today.

## Slide 8
STARTUPLAB
PROJECT PROGRESS
08
Approved changes and key decisions
Show how approved changes affected the final scope, schedule, or solution.
Reference | Change or Decision | Approved By / Date | Effect on Project | Current Status
ADD-001 | SME/Individual/Collateral addendum: Field Visit form replaces CI & References; CM/REM inspections now support multiple vehicles/properties. | Approved post-review | Expanded UAT scope by 14 cases (UAT-097–110) | Incorporated in UAT Plan
Material commitments require the required internal approval, including CEO approval when applicable.
Notes: HOW TO USE THIS SLIDE
Include only approved changes and decisions relevant to the final solution or UAT. Keep unapproved requests in the issue and action log.
SUGGESTED CLIENT-FACING WORDING
These approved changes explain how the final solution differs from the original plan. The UAT scope already reflects these decisions.

## Slide 9
STARTUPLAB
UAT CYCLE
09
UAT objective and decision required
Clarify what the client is validating and the decision expected at the end of the cycle.
Confirm the platform performs onboarding, underwriting, committee review, release, collections, accounting, admin, and access control correctly, before handover.
CLIENT VALIDATES
• Agreed business workflows
• Correct outputs and data behavior
• User roles and access
• Known limitations
DECISION AT THE END
To be determined at the end of the UAT cycle
UAT confirms the agreed solution. It does not provide automatic approval for new scope.
Notes: HOW TO USE THIS SLIDE
Use this transition slide before readiness and testing. Make the expected decision explicit.
SUGGESTED CLIENT-FACING WORDING
UAT allows your authorized users to confirm that the agreed solution works for the approved business processes. At the end, we will record the acceptance status and any remaining actions.

## Slide 10
STARTUPLAB
UAT CYCLE
10
UAT readiness confirmation
Confirm that the system, people, data, and documents are ready before client testing begins.
Readiness Check | Owner | Status | Evidence / Remaining Action
Internal testing completed | Rovick Romasanta | Ready | Internal QA + E2E lifecycle simulation completed (14 modules)
Critical defects resolved | Rovick Romasanta | Ready | No open critical defects on record
UAT environment available | Rovick Romasanta | Read | Staging URL / build / version TBD
Test users and roles verified | Rovick Romasanta | Ready | Role accounts provisioned for all tested roles
Test data loaded and checked | Rovick Romasanta | Pending confirmation | Sample data approval & UAT load status TBD
UAT forms and evidence folder ready | Rovick Romasanta | Ready | Appendix B (110 cases) + Appendix C issue log ready
Do not start affected tests when a critical readiness item remains unresolved.
Notes: HOW TO USE THIS SLIDE
Update the status immediately before the meeting. If an item is not ready, state its effect and the revised testing plan.
SUGGESTED CLIENT-FACING WORDING
Before testing begins, we will confirm each readiness item. Any critical gap will be resolved or the affected scenario will be rescheduled.

## Slide 11
STARTUPLAB
UAT CYCLE
11
Test users, access, and data
Confirm who will test, what access they have, and what data supports the scenarios.
Control | Planned / Expected | Actual / Verified | Client Confirmation
Authorized testers | Client testers per module (from Client Main Contact) | Pending submission | Confirm
Access levels | Role-based permissions per assigned module | Applied on load | Confirm
Approved data source | Client-approved UAT sample data set | Applied on load | Confirm
Record counts | To match approved sample data | Applied on load | Confirm
Important totals | To match approved sample data | Pending load | Confirm
Sensitive data controls | Masking / non-production values only | Applied on load | Acknowledge
Never guess missing client data. Record gaps and ask the authorized client owner to confirm the correct value.
Notes: HOW TO USE THIS SLIDE
Use totals and sample records to show that the correct data was loaded. Do not expose passwords or unnecessary sensitive information.
SUGGESTED CLIENT-FACING WORDING
We prepared the users and test data based on the approved records. Please confirm the roles, source file, counts, and important totals before we execute the scenarios.

## Slide 12
STARTUPLAB
UAT CYCLE
12
UAT scenarios and expected results
List the business tasks that client users will perform.
UAT ID | Business Scenario | Tester / Role | Expected Result | Priority
UAT-009 | Start a new Seafarer loan application | Borrower | Draft application created; navigates to workspace | Critical
UAT-028 | Endorse an application to CIG | CSA | Status → 'For Verification'; file moves to CIG queue | Critical
UAT-038 | Record an Approve vote | Credit Committee Member | Vote recorded as Approved; tally increments | Critical
UAT-060 | Create a DCR with payment allocation | Collector | DCR submitted; forwarded to AR for verification | Critical
UAT-091 | Borrower cannot access CSA portal | Any role | Access blocked; redirected to /borrower | Critical
5 representative scenarios shown; the full 110-case set across 14 modules is in Appendix B of the UAT Plan (POL-006).
Notes: HOW TO USE THIS SLIDE
Use the full UAT document for detailed steps. This slide gives the client a clear testing map.
SUGGESTED CLIENT-FACING WORDING
These are the business scenarios we agreed to validate. Each tester will complete the assigned task and confirm whether the actual result matches the expected result.

## Slide 13
STARTUPLAB
UAT CYCLE
13
UAT execution flow
Use the same five-step method for every business scenario.
1
STATE THE TASK
Confirm the business goal and expected result
2
CLIENT PERFORMS
The tester uses the system as in daily work
3
COMPARE RESULTS
Review actual result against the expected result
4
SAVE EVIDENCE
Record safe screenshots, references, or notes
5
SET STATUS
Passed, Failed, Blocked, or Pending
The client performs the test. The Project Owner facilitates, observes, records evidence, and avoids leading the result.
Notes: HOW TO USE THIS SLIDE
Display this slide before the first test case. Repeat the method when new testers join.
SUGGESTED CLIENT-FACING WORDING
For every scenario, we will state the task, let the assigned user perform it, compare the result, save appropriate evidence, and record the status together.

## Slide 14
STARTUPLAB
UAT CYCLE
14
UAT results summary
Summarize results by status and show the detailed record for important scenarios.
0
PASSED
0
FAILED
0
BLOCKED
110
PENDING
UAT ID / Scenario | Expected Result | Actual Result | Status
All 110 scenarios | Per Appendix B | Recorded during the session | Pending
Use the detailed UAT record as the source. Explain blocked tests separately from failed tests.
Notes: HOW TO USE THIS SLIDE
Populate the counts and important scenario results after testing. Do not label an unexecuted scenario as passed.
SUGGESTED CLIENT-FACING WORDING
We completed [number] scenarios. [Number] passed, while the remaining items require the actions shown in the next slide.

## Slide 15
STARTUPLAB
UAT CYCLE
15
Issues, retesting, and action plan
Separate confirmed defects from data, access, training, and new-scope concerns.
Issue ID | Type / Impact | Agreed Action | Owner | Target / Retest
UAT-025 | Defect: agent information missing from loan applications | Added staff-editable agent assignment and form display | Rovick Romasanta | Closed today
UAT-040 | Defect: committee hold could not be cleared | Added clear-hold action; return application to committee review | Rovick Romasanta | Closed today
UAT-076 | Enhancement: User Management filtering and account separation | Added role filters, pagination, and borrower/staff separation | Rovick Romasanta | Closed today
UAT-078 / 079 | Defect: deactivated account retained access | Disabled access immediately; reactivation requires fresh access | Rovick Romasanta | Closed today
UAT-094 | Defect: restricted-page message unclear | Added clear restricted-access message and safe return route | Rovick Romasanta | Closed today
Meeting follow-up | Agent dashboard showed organisation-wide Agent data | Scoped Agent dashboard analytics to the signed-in Agent | Rovick Romasanta | Closed today
Every action needs one accountable owner, a target date, and a clear condition for closure.
Notes: HOW TO USE THIS SLIDE
Review each open item with the client. State whether it affects acceptance. Escalate material commitments for CEO approval before confirming them.
SUGGESTED CLIENT-FACING WORDING
We classified each concern so the right action is clear. These are the owners, target dates, and retesting requirements agreed during the session.

## Slide 16
STARTUPLAB
UAT CYCLE
16
UAT decision and sign-off
Record one decision supported by the completed tests, evidence, and agreed actions.
ACCEPTED
ACCEPTED WITH ACTIONS
RETEST REQUIRED
NOT ACCEPTED
Decision Record | Information to Complete
Selected status | Selected at end of session
Reason | Based on recorded evidence
Acceptance conditions | Based on remaining actions, if any
Authorized client approver | Name, role, date — TBD by client
Approval evidence | Appendix G — UAT Acceptance Form
Do not pressure the client to accept critical incomplete work. Read back the decision and conditions before closing.
Notes: HOW TO USE THIS SLIDE
Select only the applicable status in the final client copy. Link the signed or written approval record after the meeting.
SUGGESTED CLIENT-FACING WORDING
Based on the completed tests and recorded evidence, the proposed UAT status is [status]. Please confirm the reason, conditions, and authorized approval record.

## Slide 17
STARTUPLAB
CLOSEOUT
17
Next steps toward final handover
Close the UAT cycle with owners, dates, and the next decision gate.
Next Step | Owner | Target Date | Completion Evidence
Send UAT summary and meeting record | Rovick Romasanta | Within 1 business day | Email to Client Main Contact
Complete remaining approved actions | Per Appendix C issue log | Per agreed retest date | Updated Appendix C entry
Retest affected scenarios | Client tester / Project Owner | Per agreed retest date | Updated Appendix B record
Secure written UAT approval | Authorized Client Approver | TBD | Appendix G, signed
Prepare final handover package | Rovick Romasanta | TBD | Handover checklist
Conduct final handover meeting | Rovick Romasanta and LSLGC | TBD | Signed handover record
The UAT cycle closes when results, actions, approval, and the next gate are documented and shared.
Notes: HOW TO USE THIS SLIDE
Confirm every owner and target date before ending. Send the written record promptly and prepare the separate final handover presentation after UAT approval.
SUGGESTED CLIENT-FACING WORDING
To close today’s UAT cycle, these are the agreed next steps, owners, and dates. I will send the written record for confirmation and prepare the final handover once the acceptance requirements are complete.