## Project Info
StartupLab Project SDLC Progress Tracker
Project Info — Overall Progress and Status pull live from Modules Progress.
Project Name | Client | Project Manager | Technical Lead | Start Date | Target Go-Live | Overall Progress | Status
Commercial Real Estate Operations Platform | Scarbrough Management Corporation | None | Johnrey | 2026-07-30 | 2026-09-28 | 92.98% | 🟢 Near Completion
POS/Inventory | JN Computer Trading OPC / PautangPC | None | Andrei | 2026-07-15 | 2026-09-15 | 64.22% | 🟡 In Progress
E-Commerce | JN Computer Trading OPC / PautangPC | None | Andrei | 2026-07-15 | 2026-09-15 | 80.14% | 🟡 In Progress
Pautang PC (upcoming) | JN Computer Trading OPC / PautangPC | None | Andrei | 2026-07-15 | 2026-09-15 | 75.83% | 🟢 Near Completion
LoanStar System | LoanStar | None | Rovick | 2026-06-01 | 2026-09-25 | 72.03% | 🟡 In Progress
Fortune Procurement System | Fortune Packaging | None | Rovick | 2026-04-23 | 2026-08-07 | 94.23% | 🟢 Near Completion
Eventuz | Wedding Ind. | None | Rovick | 2026-04-17 | 2026-06-14 | 85.29% | ✅ Completed
Cleanse&Drip | Max | None | JD | 2026-06-20 | 2026-08-01 | 94.17% | 🟢 Near Completion
Cleanse&Drip/ Marketing/Portal | Max |  | Andrei | Sept 8, 2026 |  | 0% | ✅ Completed
HRIS | Simply Source |  | Andrei | Sept 15, 2026 |  | 0% | 🔴 Delayed
LMS | Richard |  | Rovick |  |  | 0% | 🔴 Delayed
Anna's Project | Anna Sotto |  | Sheila |  |  | 0% | 🔴 Delayed
StepUp | Fortune Packaging | None | JD | 2026-02-02 | 2026-08-07 | 100% | ✅ Completed
Ayos | Gov |  | Sheila |  |  | 0% | 🔴 Delayed
Maintenance
LMS | PelvicGlobal | None | Andrei |  |  | 0% | 🔴 Delayed
POS | Anne | None | JD |  |  | 0% | 🔴 Delayed
Pelvic enhancement | PelvicGlobal |  | JD | 2026-08-07 | 2026-08-16 | 0% | ✅ Completed
Opportunities
LMS for startuplab | GP Leadership | None
HRIS | Shachar | None
Note: | Blue = edit here. Overall Progress/Status are formulas — add project rows in Modules Progress to feed them.

## Roles Commitments
Name | Roles | Check status after 1 month 9-6-2026
Johnrey | AI+ Cybersecurity
Andrei | AI + E-Commerce
Rovick | AI + Server Admin
JD | AI +
Sheila | AI + Solutions Architech

## Modules Progress
Project Modules Progress
One row per module/feature. Module Progress % is weighted, not averaged.
Project | Module/activities | Owner | BRD | Analysis | UI/UX Design | Development | Code Review | QA Testing | UAT | Deployment | Documentation | Maintenance | Module Progress % | Status | Remarks
Commercial Real Estate Operations Platform | Executive Dashboard | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | Property Management module | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | Lease Management module | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | Contact and Entity Management module | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | Document Management module | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | Global Search | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | Notifications and operational reminders | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | Agreed AI productivity features | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | User authentication and role management | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | Airtable data-migration tools or scripts | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
Commercial Real Estate Operations Platform | Tenant Portal | Johnrey | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 100% | 90% | 20% | 97.6% | In Progress
POS/Inventory | Product Module | Andrei | 100% | 100% | 100% | 100% | 90% | 90% | 30% | 100% | 0% | 0% | 89.5% | In Progress
POS/Inventory | Sales Module | Andrei | 100% | 100% | 100% | 100% | 90% | 70% | 30% | 100% | 0% | 0% | 87.5% | In Progress
POS/Inventory | Dashboard | Andrei | 100% | 100% | 80% | 70% | 70% | 20% | 0% | 100% | 0% | 0% | 65% | In Progress
POS/Inventory | Executive Dashboard / Reports | Andrei | 100% | 100% | 100% | 70% | 0% | 20% | 0% | 0% | 0% | 0% | 55% | In Progress
POS/Inventory | Purchase / Procurement | Andrei | 100% | 100% | 100% | 80% | 0% | 20% | 0% | 0% | 0% | 0% | 59% | In Progress
POS/Inventory | Sales Return / RMA | Andrei | 100% | 100% | 100% | 80% | 0% | 20% | 0% | 0% | 0% | 0% | 59% | In Progress
POS/Inventory | AI | Andrei | 100% | 50% | 100% | 80% | 0% | 20% | 0% | 0% | 0% | 0% | 54% | In Progress
POS/Inventory | Accounting | Andrei | 100% | 100% | 100% | 70% | 70% | 40% | 0% | 0% | 0% | 0% | 64% | In Progress
POS/Inventory | Human Resource Management | Andrei | 100% | 50% | 100% | 70% | 0% | 20% | 0% | 0% | 0% | 0% | 50% | In Progress
Pautang PC (upcoming) | Dashboard / Reports | Andrei | 100% | 100% | 100% | 100% | 80% | 60% | 0% | 0% | 0% | 0% | 79% | In Progress
Pautang PC (upcoming) | Inquiries | Andrei | 100% | 100% | 100% | 100% | 80% | 60% | 0% | 0% | 0% | 0% | 79% | In Progress
Pautang PC (upcoming) | Client Profiles | Andrei | 100% | 100% | 100% | 100% | 80% | 60% | 0% | 0% | 0% | 0% | 79% | In Progress
Pautang PC (upcoming) | Credit investigations | Andrei | 100% | 100% | 100% | 100% | 80% | 60% | 0% | 0% | 0% | 0% | 79% | In Progress
Pautang PC (upcoming) | Approvals | Andrei | 100% | 100% | 100% | 100% | 80% | 60% | 0% | 0% | 0% | 0% | 79% | In Progress
Pautang PC (upcoming) | Expenses | Andrei | 100% | 100% | 100% | 100% | 80% | 60% | 0% | 0% | 0% | 0% | 79% | In Progress
E-Commerce | Homepage & Banner Spotlight | Andrei | 100% | 100% | 90% | 90% | 80% | 60% | 0% | 0% | 0% | 0% | 74% | In Progress
E-Commerce | Product Catalog | Andrei | 100% | 100% | 90% | 90% | 60% | 60% | 0% | 0% | 0% | 0% | 72% | In Progress
E-Commerce | Product Details | Andrei | 100% | 100% | 90% | 90% | 60% | 60% | 0% | 0% | 0% | 0% | 72% | In Progress
E-Commerce | Cart & Mini-Drawer | Andrei | 100% | 100% | 90% | 90% | 60% | 60% | 0% | 0% | 0% | 0% | 72% | In Progress
E-Commerce | Checkout | Andrei | 100% | 100% | 90% | 90% | 60% | 60% | 0% | 0% | 0% | 0% | 72% | In Progress
E-Commerce | Order Tracking | Andrei | 100% | 100% | 90% | 80% | 60% | 60% | 0% | 0% | 0% | 0% | 68% | In Progress
E-Commerce | Admin Storefront Control | Andrei | 100% | 100% | 90% | 70% | 60% | 60% | 0% | 0% | 0% | 0% | 64% | In Progress
Cleanse&Drip | Intake Form | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 95% | In Progress
Cleanse&Drip | Client Feedback | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 95% | In Progress
Cleanse&Drip | Role based Dashboard | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 95% | In Progress
Cleanse&Drip | Appointments | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 95% | In Progress
Cleanse&Drip | Inventory | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 95% | In Progress
Cleanse&Drip | Finance | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 95% | In Progress
Fortune Procurement System | Purchase Requisition (PR1) Intake | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 95% | Ready for Deployment
Fortune Procurement System | PR2 Planning & Classification | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Approvals Workflow | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Canvassing & RFQ | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Purchase Orders | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Supplier Accounts & Accreditation | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Supplier Portal (Quotes/PO/Deliveries) | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Compliance Documents | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Delivery Tracking | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Warehouse Validation & Receiving | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Goods Receipt (GRN) | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | TSQA (Quality Assurance) | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Fortune Procurement System | Substitute Review | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0% | 92.5% | Ready for Deployment
Eventuz | Event Setup | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
Eventuz | Ticket Type & Pricing Management | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
Eventuz | Seating & Floor Plan Design | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
Eventuz | Registration & Checkout (Payment) | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
Eventuz | Seat Assignment | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
Eventuz | Ticket Issuance & QR Delivery | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
Eventuz | Attendee / Guest Management | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
Eventuz | Check-in / QR Scanning | Rovick | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
LoanStar System | Borrower Portal | Rovick | 92% | 85% | 100% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 61.1% | In Progress
LoanStar System | Leads | Rovick | 92% | 70% | 100% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 59.6% | In Progress
LoanStar System | Intake | Rovick | 92% | 90% | 100% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 61.6% | In Progress
LoanStar System | Computation | Rovick | 92% | 90% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 59.6% | In Progress
LoanStar System | Verification (CIG) | Rovick | 92% | 95% | 100% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 62.1% | In Progress
LoanStar System | Committee | Rovick | 92% | 95% | 100% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 62.1% | In Progress
LoanStar System | Negotiation | Rovick | 92% | 95% | 100% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 62.1% | In Progress
LoanStar System | Release (LRA) | Rovick | 92% | 95% | 100% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 62.1% | In Progress
LoanStar System | Accounting (AR) | Rovick | 92% | 95% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 60.1% | In Progress
LoanStar System | Collection | Rovick | 92% | 95% | 100% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 62.1% | In Progress
LoanStar System | Remedial | Rovick | 92% | 95% | 100% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 62.1% | In Progress
StepUp | Recruitment | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
StepUp | HR Management | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
StepUp | Performance Appraisal | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
StepUp | Trainings | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
StepUp | Announcements | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
StepUp | Dashboard | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
StepUp | Leave Managemenent | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
StepUp | SMTP | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
Pelvic enhancement | Payment Failed Automation | JD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed
Cleanse&Drip/ Marketing/Portal | dada | Andrei | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In Progress
Cleanse&Drip/ Marketing/Portal | dasdsa | Andrei | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In Progress
|  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
Note: | Enter phase completion 0-100% per module. Module Progress % and colors calculate automatically.

## Project Summary
Project Summary
Auto-summarized from Modules Progress.
Project Name | Total Modules | Completed | In Progress | Not Started | Overall Progress | Health
Commercial Real Estate Operations Platform | 11 | 0 | 11 | 0 | 92.98% | 🟢
POS/Inventory | 9 | 0 | 9 | 0 | 64.22% | 🟡
E-Commerce | 7 | 0 | 7 | 0 | 80.14% | 🟡
Pautang PC (upcoming) | 6 | 0 | 6 | 0 | 75.83% | 🟢
LoanStar System | 11 | 0 | 11 | 0 | 72.03% | 🟡
Fortune Procurement System | 13 | 0 | 13 | 0 | 94.23% | 🟢
Eventuz | 8 | 8 | 0 | 0 | 85.29% | ✅
Cleanse&Drip | 6 | 0 | 6 | 0 | 94.17% | 🟢
StepUp | 8 | 8 | 0 | 0 | 100% | ✅
Ayos | 0 | 0 | 0 | 0 | 0% | 🔴
Maintenance | 0 | 0 | 0 | 0 | 0% | 🔴
LMS | 0 | 0 | 0 | 0 | 0% | 🔴
POS | 0 | 0 | 0 | 0 | 0% | 🔴
Pelvic enhancement | 1 | 1 | 0 | 0 | 0% | ✅
Opportunities | 0 | 0 | 0 | 0 | 0% | 🔴
LMS for startuplab | 0 | 0 | 0 | 0 | 0% | 🔴
Note: | All columns are formulas driven off Modules Progress — nothing to type here.

## SDLC Weight
SDLC Weight
Single source of truth for phase weighting — change here and every Module Progress % updates.
SDLC Phase | Weight
Business Requirements (BRD) | 5%
System Analysis | 10%
UI/UX Design | 10%
Development | 40%
Code Review | 10%
QA Testing | 10%
User Acceptance Testing (UAT) | 5%
Deployment | 5%
Documentation | 3%
Maintenance / Hypercare | 2%
TOTAL | 100%
Note: | Weights must total 100% — the TOTAL cell will flag if they don't.

## Gantt Timeline
Illustrative weekly view — shade the weeks each module is active.
Project | Module | Jan W1 | Jan W2 | Jan W3 | Jan W4 | Feb W1 | Feb W2 | Feb W3 | Feb W4 | Mar W1 | Mar W2 | Mar W3 | Mar W4 | Apr W1 | Apr W2 | Apr W3 | Apr W4 | May W1 | May W2 | May W3 | May W4 | Jun W1 | Jun W2 | Jun W3 | Jun W4 | Jul W1 | Jul W2 | Jul W3 | Jul W4 | Aug W1 | Aug W2 | Aug W3 | Aug W4 | Sept W1 | Sept W2 | Sept W3 | Sept W4
Commercial Real Estate Operations Platform | System Analysis
Commercial Real Estate Operations Platform | Executive Dashboard
Commercial Real Estate Operations Platform | Property Management module
Commercial Real Estate Operations Platform | Lease Management module
Commercial Real Estate Operations Platform | Contact and Entity Management module
Commercial Real Estate Operations Platform | Document Management module
Commercial Real Estate Operations Platform | Global Search
Commercial Real Estate Operations Platform | Notifications and operational reminders
Commercial Real Estate Operations Platform | Agreed AI productivity features
Commercial Real Estate Operations Platform | User authentication and role management
Commercial Real Estate Operations Platform | Airtable data-migration tools or scripts
Commercial Real Estate Operations Platform | Code Review
Commercial Real Estate Operations Platform | QA Testing
Commercial Real Estate Operations Platform | UAT
Commercial Real Estate Operations Platform | Deployment
Commercial Real Estate Operations Platform | Documentation
Commercial Real Estate Operations Platform | Maintenance (warranty after deployment)
POS/Inventory | Product Module
POS/Inventory | Sales Module
POS/Inventory | Dashboard
POS/Inventory | Executive Dashboard / Reports
POS/Inventory | Purchase / Procurement
POS/Inventory | Sales Return / RMA
POS/Inventory | AI
POS/Inventory | Accounting
POS/Inventory | Human Resource Management
POS/Inventory | Code Review
POS/Inventory | QA Testing
POS/Inventory | UAT internal, external
POS/Inventory | Deployment
POS/Inventory | Documentation
POS/Inventory | Maintenance (warranty after deployment)
Pautang PC (upcoming) | System Analysis
Pautang PC (upcoming)
Pautang PC (upcoming)
Pautang PC (upcoming)
Pautang PC (upcoming)
Pautang PC (upcoming)
Pautang PC (upcoming) | Code Review
Pautang PC (upcoming) | QA Testing
Pautang PC (upcoming) | UAT internal, external
Pautang PC (upcoming) | Deployment
Pautang PC (upcoming) | Documentation
Pautang PC (upcoming) | Maintenance (warranty after deployment)
E-Commerce | Homepage & Banner Spotlight
E-Commerce | Product Catalog
E-Commerce | Product Details
E-Commerce | Cart & Mini-Drawer
E-Commerce | Checkout
E-Commerce | Order Tracking
E-Commerce | Admin Storefront Control
E-Commerce | Code Review
E-Commerce | QA Testing
E-Commerce | UAT internal, external
E-Commerce | Deployment
E-Commerce | Documentation
E-Commerce | Maintenance (warranty after deployment)
Cleanse&Drip | System Analysis
Cleanse&Drip | Intake Form
Cleanse&Drip | Client Feedback
Cleanse&Drip | Role based Dashboard
Cleanse&Drip | Appointments
Cleanse&Drip | Inventory
Cleanse&Drip | Finance
Cleanse&Drip | Code Review
Cleanse&Drip | QA Testing
Cleanse&Drip | UAT internal, external
Cleanse&Drip | Deployment
Cleanse&Drip | Documentation
Cleanse&Drip | Maintenance (warranty after deployment)
Stepup | System Analysis
Stepup | Intake Form
Stepup | Client Feedback
Stepup | Role based Dashboard
Stepup | Appointments
Stepup | Inventory
Stepup | Finance
Stepup | Code Review
Stepup | QA Testing
Stepup | UAT internal, external
Stepup | Deployment
Stepup | Documentation
Stepup | Maintenance (warranty after deployment)
Eventuz | Event Setup
Eventuz | Ticket Type & Pricing Management
Eventuz | Seating & Floor Plan Design
Eventuz | Registration & Checkout (Payment)
Eventuz | Seat Assignment
Eventuz | Ticket Issuance & QR Delivery
Eventuz | Attendee / Guest Management
Eventuz | Check-in / QR Scanning
Eventuz | Code Review
Eventuz | QA Testing
Eventuz | UAT internal, external
Eventuz | Deployment
Eventuz | Documentation
Eventuz | Maintenance (warranty after deployment)
Fortune Procurement System | Purchase Requisition (PR1) Intake
Fortune Procurement System | PR2 Planning & Classification
Fortune Procurement System | Approvals Workflow
Fortune Procurement System | Canvassing & RFQ
Fortune Procurement System | Purchase Orders
Fortune Procurement System | Supplier Accounts & Accreditation
Fortune Procurement System | Supplier Portal (Quotes/PO/Deliveries)
Fortune Procurement System | Compliance Documents
Fortune Procurement System | Delivery Tracking
Fortune Procurement System | Warehouse Validation & Receiving
Fortune Procurement System | Goods Receipt (GRN)
Fortune Procurement System | TSQA (Quality Assurance)
Fortune Procurement System | Substitute Review
Fortune Procurement System | Code Review
Fortune Procurement System | QA Testing
Fortune Procurement System | UAT internal, external
Fortune Procurement System | Deployment
Fortune Procurement System | Documentation
Fortune Procurement System | Maintenance (warranty after deployment)
Loanstar | SA
Loanstar | Borrower Portal
Loanstar | Leads
Loanstar | Intake
Loanstar | Computation
Loanstar | Verification (CIG)
Loanstar | Committee
Loanstar | Negotiation
Loanstar | Release (LRA)
Loanstar | Accounting (AR)
Loanstar | Collection
Loanstar | Remedial
Loanstar | Code Review
Loanstar | QA Testing
Loanstar | UAT internal, external
Loanstar | Client Meeting
Loanstar | Deployment
Loanstar | Documentation
Loanstar | Maintenance (warranty after deployment)

## Reference
Reference
Status | Definition
Not Started | Work has not yet begun.
In Progress | Work is actively being completed.
For Review | Waiting for technical or business review.
Blocked | Progress cannot continue due to a dependency or issue.
For QA | Ready for Quality Assurance testing.
For UAT | Ready for User Acceptance Testing.
Ready for Deployment | Approved and waiting for deployment.
Completed | Module has completed all SDLC phases, including documentation and deployment.
Traffic Light Indicator
Overall Progress | Indicator
0-30% | 🔴 Delayed
31-70% | 🟡 In Progress
71-99% | 🟢 Near Completion
100% | ✅ Completed
Why This Design Works
• Multiple developers can work across multiple projects at once.
• Module-level visibility, not just one project percentage.
• Overall project progress is derived automatically from module data.
• Aligns with SDLC process and Agile ceremonies.
• Can be imported into a future BI dashboard with minimal changes.

## Team Update Guidelines
Team Update Guidelines
Objective
Standardized way for project owners to report progress so management has real-time visibility across all active projects.
General Guidelines
• Each Project Owner keeps the tracker up to date.
• Update at least every Friday before the Weekly Scrum, or right after a major milestone.
• Progress reflects actual completed work, not estimates.
• Each module has exactly one assigned owner.
• Keep supporting evidence (Jira, PRs, UAT reports, deployment records) available if requested.
How to Update Each SDLC Phase
BRD | 0-100% based on completion of business requirements and stakeholder approval.
System Analysis | Based on completed workflows, process analysis, use cases, technical requirements.
UI/UX Design | Based on approved wireframes, mockups, or design prototypes.
Development | % of coding completed for the module.
Code Review | Update after peer review or technical lead approval.
QA Testing | Update after completed functional, regression, or integration testing.
UAT | Update after successful business user validation and acceptance.
Deployment | Update after deployment to the target environment and validation.
Documentation | Update once technical docs, user guides, or release notes are done.
Maintenance / Hypercare | Update after post-deployment monitoring and stabilization.